## Toolkit
Overseas School Trip Planning Toolkit
© Voyager School Travel
TIMELINE | TASK | OWNER | DUE DATE | STATUS | TOP TIPS | USEFUL LINKS & DOCUMENTS | TRAVEL PARTNER RESPONSIBILITIES | AMENDMENTS & CANCELLATIONS
>12 MONTHS BEFORE THE TRIP | TRIP PROPOSAL Meet with Headteacher to discuss your overseas educational visit. | Trip Leader & Headteacher |  | Not Started | Proposal to include: objective, destination, dates, number of students, year group & estimated budget per person. | ✎ Proposal for an overseas residential trip | Voyager School Travel can provide you with an indicative budget to support your proposal. | Your have total flexibility at this stage
| PLANNING MEETING WTH EVC & FINANCE The EVC will guide you through the school's policies, checks & risk assessment paperwork. Finance can help cost the trip and manage the payment side. | Trip Leader & EVC Finance/Bursar |  | Not Started | Check the school's policy for pupil:staff ratios, and how cover will be funded, as this might impact your budget. 💡Ask about the availability of grants & funding for school trips. | Ways to fund your school trip
| HEAD / GOVERNOR APPROVAL TO LAUNCH THE TRIP | Trip Leader, SLT & Governors |  | Not Started
| ENLIST COLLEAGUES & OTHER DEPARTMENTS If you have a co-ed group you will need both male and female staff in the group. Try to enlist a trained first aider. | Trip leader |  | Not Started | Can you include other departments and make it a cross-curricular trip?
| ENTER ONTO THE SCHOOL CALENDAR | Trip leader |  | Not Started | Make sure no-one else nabs your dates!
| GENERATE INITIAL INTEREST Drum up interest from students & parents to estimate the take-up | Trip leader |  | Not Started | Talk to students at assembly or in lesson time. Create posters to advertise the trip Email parents and hold a parent evening. | Posters, letters and permission slip templates
12 MONTHS BEFORE THE TRIP | CONSULT WITH EDUCATIONAL TRAVEL PROVIDER(S) Advise them of your learning objectives, activities and excursions, expected group size and budget. Don’t forget to include special requirements such as wheelchair access. | Trip leader & travel company |  | Not Started | 💡 Half of all overseas school trips are taken between May & July! For the best deals & availability avoid travelling in these months. | Why use a travel partner? | Voyager School Travel can provide a quick indication of budget & availability, or a formal quote with reservations.
| REVIEW TRAVEL COMPANY PROPOSALS Compare suggested itinerary, price breakdown & inclusions. Check provider's online reviews, accreditation & financial protection | Trip Leader |  | Not Started | Pay special attention to what is and isn't included in the price. Check if accommodation & transport is reserved for your group or 'subject to availability' | ABTA, ATOL and choosing the right travel partner | Voyager School Travel's quotes are valid 14 days. Your accommodation & transport will be held for you over this period.
| APPOINT PROVIDER & MAKE A PROVISIONAL BOOKING Review your provisional booking details & payment schedule | Trip leader & travel company |  | Not Started | You need to move quickly at this point because your travel company may only be able to hold flights or accommodation for a limited time. |  | A provisional booking means your trip is reserved, pending your deposits.
| MEET WITH FINANCE/BURSAR Agree with Finance who will collect deposits from the parents. Check the payment schedule works with school holiday dates & remittance processes. | Trip Leader & Finance/Bursar |  | Not Started | 💡 Add a small contingency to the price in case plans change. Don't forget that students will need to bring some spending pocket money too. |  | Voyager will advise what needs to paid for locally e.g. meals en route, tourist taxes, damage deposits & some visits. | Any additional adults will be charged for
| LAUNCH YOUR TRIP TO STUDENTS & PARENTS Parent letter/email to include payment deadlines, reply slip & consent form. | Trip leader |  | Not Started | Decide on your waiting list or ballot policy in case your trip is oversubscribed. | Posters, letters and permission slip templates
| SIGN UP STUDENTS & COLLECT DEPOSITS Review your group to see if you need additional staff e.g. for SEND pupils. | Trip Leader & Finance/Bursar |  | Not Started |  | Article on how to fill your school trip |  | Your tour price is based on your estimated group size. Your group could pay more if numbers drop.
AT LEAST 10 MONTHS BEFORE THE TRIP | CONFIRM FINAL NUMBERS TO THE TOUR OPERATOR Confirm final numbers and give notice of any accessibility requirements so your provider can request accessible rooms, transport or additional assistance | Trip Leader |  | Not Started | 💡Travelling to Europe is a little different these days. Check that everyone has an up-to-date passport & EHIC. Give parents plenty of time for passport & visa applications. | Latest Travel Rules for School Trips to Europe | Once final numbers are confirmed Voyager will send an invoice for the first deposits & payment schedule for the remainder.
| PAY TRIP DEPOSITS TO THE TOUR OPERATOR Secure your booking with a deposit & receive your confirmation pack. Make note of when future payments are required. | Trip Leader & Finance/Bursar Tour Operator |  | Not Started | Check your booking confirmation paperwork carefully and let your provider know of any omissions or changes. |  | Voyager School Travel will confirm & pay for your transport & accommodation at this stage. | Deposits paid are non-refundable. The tour price may change if a student drops out or an additional adult is added from now on.
| SET UP THE TRIP ON EVOLVE (IF USING) Register your trip on Evolve and add relevant docs such as staff lists, passenger lists & risk assessments. | Trip Leader or EVC |  | Not Started | Many schools use the EVOLVE online tool to manage overseas trips. |  | All Voyager School Travel's recommended accommodation is audited for suitability for school groups.
| CARRY OUT RISK ASSESSMENTS Work with the EVC to assess potential risks bearing in mind the children in your group. | Trip Leader and EVC |  | Not Started | Your EVC can help you assess and manage potential risks and provide examples of previous risk assessments and emergency response plans. 💡Talk to your travel provider about visiting the resort in advance so you can conduct your own risk assessment in situ | Resources for your risk assessment | Voyager holds the LOtC Quality Badge which means you can be sure of the safety of our provision. To carry out a subsidised inpection visit https://www.voyagerschooltravel.com/teacher-zone/book-an-inspection-visit/
3 MONTHS BEFORE DEPARTURE | MAKE FINAL PAYMENTS | Finance/Bursar or Admin Support |  | Not Started |  |  |  | A sliding scale of cancellation charges now apply.
| FINALISE YOUR ITINERARY Work with the travel company to confirm the final details such as detailed timings of meals & excursions. | Trip Leader |  | Not Started | At Voyager, an experienced tour coordinator will plan the itinerary to make sure students get the most from every visit |  | Voyager will book & pay for any remaining items such as visits, guides & activities. | Any additions to your itinerary could change your tour price.
| COLLECT PASSENGER DETAILS & SEND TO TOUR OPERATOR Send passenger details to the travel company including: Passport details Gender breakdown Dietary, medical and accessibility requirements | Trip Leader or Admin support |  | Not Started | This is your last chance to check if anyone needs a visa or new passport to enter your destination country. 💡Take a photo of each passport for reference | Latest Travel Rules for School Trips to Europe | Voyager School Travel will need your names list to finalise travel arrangements, visits & activities. | Airlines will charge a fee for changing passenger passport details so please be careful when completing the nominal roll!
| ALLOCATE ROOMS Depending on gender breakdowns & student preferences. Split the children into sub-groups & allocate a teacher to each group | Trip Leader |  | Not Started | Use your experience of the children or ask them to nominate 4 people they'd be happy to share with & commit to having at least one in the dorm. Bear in mind that friendship groups can change in the build-up to the trip! | Student code of conduct for school trips | Voyager School Travel will send you your room allocations when supplied by the accommodation provider. This is likely to be around 2 weeks to departure.
2 WEEKS TO GO | REVIEW FINAL PACK FROM TOUR OPERATOR Check you have received all your travel and insurance documents from your provider. | Trip Leader |  | Not Started |  |  | Voyager will send your itinerary, tickets, boarding passes, vouchers, driver details & emergency contact numbers.
| BRIEF PARENTS Include pick up times, packing list, mobile phone policy, spending money & emergency contact details. | Trip Leader |  | Not Started | 💡Advise parents where they can see trip updates e.g. your school's Facebook page | Essential packing list
| SENCO MEETING Are there any additional considerations to be aware of? | Trip Leader & SENCO |  | Not Started |  |  |  | Any additional adults, on top of your free teacher ratio, will be charged for
| SCHOOL NURSE MEETING Does anyone in the group have a medical condition? | Trip Leader & School Nurse |  | Not Started | 💡Bring relevant doctor numbers and medicines on the trip
| BRIEF CARETAKER / PREMISES MANAGER Advice the caretaker of coach pick up & drop off times - especially if the trip is out of school hours. | Trip Leader & Caretaker |  | Not Started | Is there access for the coach? Can the toilets & car park be made available on the day of departure and return? Advise the caretaker which staff will leave their car in the carpark for the duration of the trip.
| FINAL GO AHEAD FROM HEAD / GOVERNORS If using, the Evolve platform can be used to sign off the trip. | Trip Leader & SLT |  | Not Started | Demonstrate that all details have been considered & risks mitigated in order to receive final sign off for the trip.
1 WEEK TO GO | PREPARE A LETTER OF INTRODUCTION (EU TRIPS) Some European border officials and historic sites require a letter explaining that the group is on a school trip. | Headteacher's PA |  | Not Started | Printed on headed paper & signed by the head of the school. Include the full name, nationality, date & place of birth of all the children on the trip. | ✎Samples entry letters for French border, Italy & Greece
| PAPERWORK TO TAKE WITH YOU - Travel documents (see final pack contents above) - Photo of each passport - Names list, dietary requirements, room breakdowns - Letter of introduction (see above) | Trip Leader & other staff on the trip |  | Not Started | Make copies for each staff member. | Latest Travel Rules for School Trips to Europe
| PACK YOUR TRAVEL ESSENTIALS KIT - Bin liners, tissues, hand sanitiser, sanitary towels - First aid kit, travel sickness medication & sick bags - Currency and credit card - Pupil medication - Emergency contact cards | Trip Leader |  | Not Started | 💡Give all students a laminated emergency contact card written in the destination language. | ✎Emergency contact card template
| UPDATE THE ATTENDANCE OFFICER / HEAD OF YEAR Email the Attendance Officer with the names of children on the trip. | Trip Leader & Attendance Officer |  | Not Started
DEPARTURE DAY | DOWNLOAD THE FERRY APP & CHECK IN YOUR GROUP Cross-channel groups will need to enter their group's passport details on the ferry app |  |  | Not Started | 💡Don't press submit on the ferry app until you've entered the last passenger - this includes the driver's passport details! | How to use the ferry apps | Voyager School Travel will send you instructions on how to use the relevant ferry app.
| ENJOY YOUR TRIP! |  |  | Not Started | By following this checklist, you can relax knowing that you are fully prepared. |  | Voyager School Travel are on call 24/7 if you have an emergency.
ON RETURN | EVALUATION Review the organisational aspects of the trip Were learning objectives met? Share any feedback & suggestions with your travel partner | Trip Leader |  | Not Started | You also might want to ask the children to evaluate the trip using a Google survey. | The educational benefits of language trips | Voyager School Travel will be in touch to find out how you got on and to start planning next year's trip.
© 2025 Voyager School Travel. The toolkit is for school use only. Reproduction of its content for commercial purposes is strictly prohibited.

## Checklist
Overseas School Trip Final Checklist
TIMELINE | TASK | DUE DATE | STATUS
>12 MONTHS BEFORE THE TRIP | TRIP PROPOSAL |  | In Progress
| PLANNING MEETING WTH EVC & FINANCE |  | Complete
| HEAD / GOVERNOR APPROVAL TO LAUNCH THE TRIP |  | Not Started
| SIGN UP COLLEAGUES |  | Not Started
| ENTER TRIP ONTO SCHOOL CALENDAR |  | Not Started
| GENERATE INITIAL INTEREST |  | Not Started
12 MONTHS BEFORE THE TRIP | IDENTIFY & BRIEF TOUR OPERATORS |  | Not Started
| REVIEW TRAVEL COMPANY PROPOSALS |  | Not Started
| APPOINT PROVIDER & MAKE A PROVISIONAL BOOKING |  | Not Started
| AGREE PAYMENT PROCESS WITH FINANCE/BURSAR |  | Not Started
| LAUNCH TRIP TO STUDENTS & PARENTS |  | Not Started
| SIGN UP STUDENTS & COLLECT DEPOSITS |  | Not Started
AT LEAST 10 MONTHS BEFORE THE TRIP | CONFIRM FINAL NUMBERS TO THE TOUR OPERATOR |  | Not Started
| PAY TRIP DEPOSITS TO THE TOUR OPERATOR |  | Not Started
| SET UP THE TRIP ON EVOLVE (IF USING) |  | Not Started
| COMPLETE RISK ASSESSMENTS |  | Not Started
3 MONTHS BEFORE | MAKE FINAL PAYMENTS |  | Not Started
| FINALISE ITINERARY |  | Not Started
| COLLECT PASSENGER DETAILS & SEND TO TOUR OPERATOR |  | Not Started
| ALLOCATE ROOMS |  | Not Started
2 WEEKS TO GO | REVIEW FINAL PACK FROM TOUR OPERATOR |  | Not Started
| BRIEF PARENTS |  | Not Started
| MEET SENCO |  | Not Started
| SCHOOL NURSE MEETING |  | Not Started
| BRIEF CARETAKER / PREMISES MANAGER |  | Not Started
| RECEIVE FINAL GO AHEAD FROM HEAD / GOVERNORS |  | Not Started
1 WEEK TO GO | WRITE LETTER OF INTRODUCTION (EU TRIPS) |  | Not Started
| CHECK PAPERWORK FOR TRIP |  | Not Started
| PACK TRAVEL ESSENTIALS KIT |  | Not Started
| UPDATE THE ATTENDANCE OFFICER / HEAD OF YEAR |  | Not Started
TRIP DAY | DOWNLOAD THE FERRY APP & CHECK IN GROUP |  | Not Started
| DEPART! |  | Not Started
RETURN | EVALUATION |  | Not Started
© 2025 Voyager School Travel. For school use only. Reproduction for commercial purposes is strictly prohibited